## Features Burndown
			Sprint
Feature	Completed	Efforts	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
		Burndown Baseline	645.00	614.80	584.60	554.40	524.20	494.00	463.80	433.60	403.40	373.20	343.00	312.80	282.60	252.40	222.20	192.00	161.80	131.60	101.40	71.20	41.00	10.80	0.00
		Actual	645	601	544	494
AI	0.90	63		23	26	8
AO + DO output	0.25	52			13
Control Algo (PID)	0.15	140				21
Failsafe	0.00	8
Timer-ed Relay	0.00	5
Soft Start	0.00	8
Input Math Algo	0.00	8
Fuzzy Overshoot suppression	0.00	3
Accutune	0.00	13
SP Ramp/Program/Rate	0.25	20		5
Auxiliary outputs	0.00	8
Alarm and display	0.00	20
DI function	0.00	13
Modbus, Ethernet	0.65	10		7
GUI	0.00	43
PIE Upgrading	0.00	20
IOS Client	0.38	130		10	18	21
FCT (Inc. ICT?)	0.00	17
Firmware Upgrade (Device + IOS work)	0.00	48
Self Test (Power-Up, Backgroud, Status Test)	0.00	16
		645	0	44	57	50

				Velocity	Last Sprint	Remaining	Curr Sprint	11
				50	22	11
				30	30	19

## Sprint Burn Up
Sprint	FW	IOS	SUM
9	34	10	44
10	39	18	57
11	29	21	50
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## burndown-csv
Sprint	Baseline	Actual
8	645.00	645
9	614.80	601
10	584.60	544
11	554.40	494
12	524.20
13	494.00
14	463.80
15	433.60
16	403.40
17	373.20
18	343.00
19	312.80
20	282.60
21	252.40
22	222.20
23	192.00
24	161.80
25	131.60
26	101.40
27	71.20
28	41.00
29	10.80
30	0.00

## feature-list-csv
Feature	Completed	Efforts
AI	0.90	63
AO + DO output	0.25	52
Control Algo (PID)	0.15	140
Failsafe	0.00	8
Timer-ed Relay	0.00	5
Soft Start	0.00	8
Input Math Algo	0.00	8
Fuzzy Overshoot suppression	0.00	3
Accutune	0.00	13
SP Ramp/Program/Rate	0.25	20
Auxiliary outputs	0.00	8
Alarm and display	0.00	20
DI function	0.00	13
Modbus, Ethernet	0.65	10
GUI	0.00	43
PIE Upgrading	0.00	20
IOS Client	0.38	130
FCT (Inc. ICT?)	0.00	17
Firmware Upgrade (Device + IOS work)	0.00	48
Self Test (Power-Up, Backgroud, Status Test)	0.00	16